## Sheet1
| January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
2022 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26
2021 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 9 | 15 | 22 | 29 | 6 | 13 | 20 | 27
Activity
Market Research
Fashion Research | [45 empty] | H | H | H | H | H
Fabric Research | H | H | [43 empty] | H | H | H | H | H
Color Research | H | H | [43 empty] | H | H | H | H | H
Collection Research | H | H | [45 empty] | H | H | H
Initial Fabric Selection | H | H | H | [44 empty] | H | H | H
Review Previous Sales | H | H | H | [44 empty] | H | H | H
Line Plan Meeting |  |  |  | H
Line Plan Approval |  |  |  |  | H
Order Fabric Sample Cuts |  |  |  |  | H | H | H | H | H
Concept Boards |  |  |  |  | H | H | H | H | H | H
Style Development | [5 empty] | H | H | H | H | H
Spec Sheet/Tech Drawings | [6 empty] | H | H | H | H
Pre-cost | [6 empty] | H | H | H | H
First Pattern/Prototype | [7 empty] | H | H | H | H
Fit Model Session | [9 empty] | H | H | H
Pattern Revisions | [10 empty] | H | H | H
Final Cost | [10 empty] | H | H | H
First Adoption | [11 empty] | H | H
Order Fabrics for Samples | [11 empty] | H | H | H | H
Revisions | [12 empty] | H | H | H | H
Final Adoption | [16 empty] | H
Review with Top Accounts | [18 empty] | H | H
Initial Sales Forecast | [20 empty] | H | H
Order Production Fabric | [19 empty] | H | H | H | H
Receive Fabric for Samples | [19 empty] | H | H | H | H
Cut and Sew Samples | [20 empty] | H | H | H | H
Line Preview (Sales Mtg) | [21 empty] | H
Grade/Production Marker | [22 empty] | H | H | H | H
Line Release (Start Selling) | [25 empty] | H
Receive Production Fabric | [25 empty] | H | H | H | H
Cut, Sew Production | [28 empty] | H | H | H | H | H | H
Sales Forecast Adjustment | [28 empty] | H
Order Additional Fabric | [29 empty] | H | H | H
Receive Additional Fabric | [35 empty] | H | H | H
Cut/Sew Additional Quantity | [36 empty] | H | H | H | H
Begin Shipping | [34 empty] | H
Complete Shipping | [46 empty] | H
Season Critique | [48 empty] | H